## Sprint Backlog
Sprint Back Log
Task ID | Task | Description | Story ID | Backlog ID | Sprint# | State | Estimate Time (Hours) | Assign to | Note
SMS Manage
T01 | Draw Usecase SMS |  |  | PB01 |  | New | 40 | Huy Hưng
T02 | Analyse and design code SMS |  |  |  |  | New | 40 | Huy Hưng
T03 | Code : Update start date and end date of single quarantee period |  | RQ04 |  | 1 | New | 10 | Hưng
T04 | Code: Set up SMS form |  |  |  | 1 | New | 2 | Hưng
T05 | Code: Send SMS |  | RQ05 |  | 1 | New | 25 | Huy
T06 | Code: Save SMS list , which have been sent for customer |  | RQ10 |  | 1 | New | 20 | Hưng
T07 | Code: View SMS list, which have been sent for customer |  |  |  | 1 | New | 10 | Hưng
T08 | Set up, update time to send SMS and time to stop send SMS |  |  |  | 1 | New | 30 | Hưng
T09 | Integrate All functions SMS | [5 empty] | 10 | Huy Hưng
T10 | Implement Unit Test , Integrated Test , System Test SMS |  |  |  | 1 | New | 30 | Huy Hưng
Customer Manage
T11 | Draw Usecase Customer Manage |  |  | PB02 |  |  | 20 | Tuấn
T12 | Analyse and design codeCustomer Manage | [5 empty] | 20 | Tuấn
T13 | Code: Import customer from excel format |  | RQ02 RQ03 |  | 1 | New | 20 | Tuấn Thắng
T14 | Code: Add new customer |  |  |  | 1 | New | 15 | Tuấn
T15 | Code: Update customer |  |  |  | 1 | New | 10 | Tuấn
T16 | Code: Disable customer |  |  |  | 1 | New | 5 | Tuấn
T17 | Code: Find Customer |  |  |  | 1 | New | 10 | Tuấn
T18 | Code: Set up time range that user can view list of customer birthday |  | RQ07 |  | 1 | New | 15 | Tuấn Thắng
T19 | Code: Print recent BirthDay Customer list |  |  |  | 1 | New | 20 | Tuấn Thắng
T20 | Code: View recent BirthDay Customer list |  |  |  | 1 | New | 5 | Tuấn Thắng
T21 | Integrate All functions Customer Manage |  |  |  | 1 | New | 5 | Tuấn Thắng
T22 | Implement Unit Test , Integrated Test , System Test Customer Manage |  |  |  | 1 | New | 20 | Tuấn Thắng
Motor Type Manage
T23 | Draw Usecase Motor type Manage |  |  | PB03 |  |  | 10 | Phúc
T24 | Analyse and design code Motor type Manage | [5 empty] | 20 | Phúc
T25 | Code: Add new motor type |  | RQ08 |  | 1 | New | 10 | Phúc Phương
T26 | Code: Update new motor type |  |  |  | 1 | New | 10 | Phúc Phương
T27 | Code: Find motor type Function |  |  |  | 1 | New | 10 | Phúc Phương
T28 | Code: Disable motor type |  |  |  | 1 | New | 10 | Phúc Phương
T29 | Integrate All functions Motor type Manage |  |  |  | 1 | New | 5 | Phúc Phương
T30 | Implement Unit Test , Integrated Test , System Test Motor type Manage |  |  |  | 1 | New | 20 | Phúc Phương
Motor Manage
T31 | Draw Usecase Motor Manage | [5 empty] | 10 | Phúc
T32 | Analyse and design code Motor Mange | [5 empty] | 20 | Phúc
T33 | Code: Create motor |  | RQ08 | PB03 | 1 | New | 10 | Phúc
T34 | Code: Update motor |  |  |  | 1 | New | 10 | Phúc
T35 | Code: Find motor Function |  |  |  | 1 | New | 5 | Phúc
T36 | Code: Disable motor type |  |  |  | 1 | New | 5 | Phúc
T37 | Code: Create new color of motor |  |  |  | 1 | New | 10 | Phúc Phương
T38 | Code: import motor from excel format | [5 empty] | 10 | Phúc Phương
T39 | Integrate All functions Motor Manage |  |  |  | 1 | New | 15 | Phúc Phương
T40 | Implement Unit Test , Integrated Test , System Test Motor Manage |  |  |  | 1 | New | 20 | Phúc Phương
All Package Comple
T41 | Imtegrate all package | [5 empty] | 30 | All Member
T42 | Implement Integrate Test | [5 empty] | 15 | All Member
T43 | Implement System Test. | [5 empty] | 25
Before start sprint
T44 | Test plan | [5 empty] | 6 | Phương
T45 | Training Plan | [5 empty] | 1 | Huy
T46 | Traning | [5 empty] | 20 | Thắng Huy
T47 | Project Plan | [5 empty] | 30 | Huy
T48 | Master Plan | [5 empty] | 10 | Huy
T49 | Analyse Data base | [5 empty] | 6 | Hưng
T50 | Draw ERD | [5 empty] | 7 | Hưng
T51 | Code SQL | [5 empty] | 20 | Hưng
T52 | main GUI | [5 empty] | 2 | Thắng
T53 | Quality Attribute | [5 empty] | 10 | Phương
T54 | Scope and Vision | [5 empty] | 3 | Phương
T55 | Constraint | [5 empty] | 3 | Phương
T56 | Customer Process | [5 empty] | 6 | Phương
T57 | Product backlog | [5 empty] | 4 | Phương
T58 | Write Sprint backlog | [5 empty] | 10 | Phương Thắng
T59 | Manage Burn Down Chart | [5 empty] | 15 | Thắng

## Release Backlog
Backlog ID | Backlog | STORY / FEATURE / REQUEST |  |  | Story ID | Priority | Business Value | Sprint# | State | Note
|  | As a/an [User role] | I want to [Goal] | So that [reason]
1 | QUẢN LÝ NHÂN VIÊN | Quản lí | Thêm nhân viên | Thêm nhân viên vào danh sách | RQ01 | 1 | cao | 1 | New
|  | Quản lí | Xóa nhân viên | Xóa nhân viên khỏi danh sách | RQ02 | 1 | cao | 1 | New
|  | Quản lí | Cập nhập thông tin | Sửa thông tin nhân viên | RQ03 | 1 | cao | 1 | New
|  | Quản lí | Đăng nhập | Đăng nhập vào hệ thống | RQ04 | 1 | cao | 1 | New
|  | Quản lí | Đăng xuất | Đăng xuất khỏi hệ thống | RQ05 | 1 | cao | 1 | New
|  | Quản lí | Đặt lại mật khẩu | Đặt lại mật khẩu khi quên | RQ06 | 1 | cao | 1 | New
|  | Nhân viên | Đăng nhập | Đăng nhập vào hệ thống | RQ12 | 2 | trung bình | 1 | New
|  | Nhân viên | Đăng xuất | Đăng xuất khỏi hệ thống | RQ13 | 2 | trung bình | 1 | New
|  | Nhân viên | Đặt lại mật khẩu | Đặt lại mật khẩu khi quên | RQ14 | 1 | cao | 1 | New
2 | QUẢN LÝ SẢN PHẢM | Quản lí | Thống kê số liệu | Thông kê doanh thu theo ngày,tháng | RQ07 | 2 | trung bình | 1 | New
|  | Quản lí | Thêm sản phẩm | Thêm vào menu | RQ09 | 2 | trung bình | 1 | New
|  | Quản lí | Xóa sản phẩm | Xóa khỏi menu | RQ10 | 2 | trung bình | 1 | New
|  | Quản lí | Cập nhập menu | Chỉnh sửa menu | RQ11 | 2 | trung bình | 1 | New
|  | Nhân viên | Thêm sản phẩm | Thêm sản phẩm vào hóa đơn | RQ17 | 2 | trung bình | 1 | New
|  | Nhân viên | Xóa sản phẩm | Xóa sản phảm trong hóa đơn | RQ18 | 2 | trung bình | 1 | New
|  | Khách hàng | Tìm kiếm sản phẩm | Tìm sản phẩm dễ dàng hơn | RQ25 | 2 | trung bình | 1 | New
|  | Khách hàng | Xem chi tiết sản phẩm | Xem sản phảm gồm thành phần gì | RQ26 | 3 | thấp | 1 | New
|  | Khách hàng | Sắp xếp danh sách sản phẩm | Sắp xếp theo danh mục như café, nước ép, … | RQ27 | 3 | thấp | 1 | New
|  | Khách hàng | Xóa sản phẩm trong giỏ hàng | Xóa sản phẩm đã thêm vào giỏ | RQ28 | 1 | cao | 1 | New
|  | Khách hàng | Thêm sản phẩm vào giỏ hàng | Thêm sản phảm vào giỏ | RQ29 | 1 | cao | 1 | New
3 | QUẢN LÝ KHÁCH HÀNG | Quản lí | Tạo mã khuyến mãi | Ưu đãi và giảm giá cho khách hàng | RQ08 | 2 | trung bình | 1 | New
|  | Nhân viên | Chat tin nhắn | Biết được nhu cẩu của khách hàng như đặt chỗ, hỏi menu,… | RQ19 | 1 | cao | 1 | New
|  | Khách hàng | Đăng ký tài khoản | Tạo tài khoản | RQ21 | 1 | cao | 1 | New
|  | Khách hàng | Đặt lại mật khẩu | Đặt lại mật khẩu khi quên | RQ20 | 1 | cao | 1 | New
|  | Khách hàng | Đăng nhập | Đăng nhập vào ứng dụng | RQ22 | 1 | cao | 1 | New
|  | Khách hàng | Đăng xuất | Đăng xuất khỏi ứng dụng | RQ23 | 1 | cao | 1 | New
|  | Khách hàng | Cập nhập thông tin | Sửa thông tin khách hàng | RQ36 | 1 | cao | 1 | New
4 | QUẢN LÝ ĐƠN HÀNG | Khách hàng | Lịch sử mua hàng | Xem hóa đơn đã đặt từ trước | RQ30 | 2 | trung bình | 1 | New
|  | Khách hàng | Hủy đơn hàng | Hủy đơn hàng khi không còn nhu cầu mua | RQ31 | 1 | cao | 1 | New
|  | Khách hàng | Thanh toán online | Thanh toán linh hoạt | RQ32 | 3 | thấp | 1 | New
|  | Khách hàng | Đặt hàng online | Đặt hàng mà không cần ra quán | RQ33 | 3 | thấp | 1 | New
|  | Khách hàng | Theo dõi đơn hàng | Theo dõi tình trạng đơn hàng | RQ34 | 1 | cao | 1 | New
|  | Khách hàng | Đánh giá và nhận xét sản phẩm | Đánh giá sản phảm sau khi mua | RQ37 | 3 | thấp | 1 | New
|  | Khách hàng | Sử dụng mã khuyến mãi | Nhận ưu đãi | RQ35 | 2 | trung bình | 1 | New
|  | Nhân viên | Lập hóa đơn | Lập hóa đơn thanh toán của khách | RQ15 | 1 | cao | 1 | New
|  | Nhân viên | Xóa hóa đơn | Xóa hóa đơn khi khách không còn nhu cầu mua | RQ16 | 1 | cao | 1 | New
|  | Nhân viên | Xác nhận mã khuyến mãi | Xác nhận ưu đãi | RQ24 | 2 | trung bình | 1 | New

## Product Backlog
Đề tài: Quản lý quán caffee
Nhóm 4
`
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
RQ01 | Quản lí | Thêm nhân viên | Thêm nhân viên vào danh sách | 1 | cao |  | Đang triển khai
RQ02 | Quản lí | Xóa nhân viên | Xóa nhân viên khỏi danh sách | 1 | cao |  | Đã hoàn thành
RQ03 | Quản lí | Cập nhập thông tin | Sửa thông tin nhân viên | 1 | cao |  | Đã hoàn thành
RQ04 | Quản lí | Đăng nhập | Đăng nhập vào hệ thống | 1 | cao |  | Đang triển khai
RQ05 | Quản lí | Đăng xuất | Đăng xuất khỏi hệ thống | 1 | cao |  | Đã hoàn thành
RQ06 | Quản lí | Đặt lại mật khẩu | Đặt lại mật khẩu khi quên | 1 | cao |  | Đã hoàn thành
RQ07 | Quản lí | Thống kê số liệu | Thông kê doanh thu theo ngày,tháng | 2 | trung bình |  | Đang phát triển
RQ08 | Quản lí | Tạo mã khuyến mãi | Ưu đãi và giảm giá cho khách hàng | 2 | trung bình |  | Đang phát triển
RQ09 | Quản lí | Thêm sản phẩm | Thêm vào menu | 2 | trung bình |  | Đang phát triển
RQ10 | Quản lí | Xóa sản phẩm | Xóa khỏi menu | 2 | trung bình |  | Đang phát triển
RQ11 | Quản lí | Cập nhập menu | Chỉnh sửa menu | 2 | trung bình |  | Đang phát triển
RQ12 | Nhân viên | Đăng nhập | Đăng nhập vào hệ thống | 2 | trung bình |  | Đang phát triển
RQ13 | Nhân viên | Đăng xuất | Đăng xuất khỏi hệ thống | 2 | trung bình |  | Đã hoàn thành
RQ14 | Nhân viên | Đặt lại mật khẩu | Đặt lại mật khẩu khi quên | 1 | cao |  | Đã hoàn thành
RQ15 | Nhân viên | Lập hóa đơn | Lập hóa đơn thanh toán của khách | 1 | cao |  | Chưa bắt đầu
RQ16 | Nhân viên | Xóa hóa đơn | Xóa hóa đơn khi khách không còn nhu cầu mua | 1 | cao |  | Chưa bắt đầu
RQ17 | Nhân viên | Thêm sản phẩm | Thêm sản phẩm vào hóa đơn | 2 | trung bình |  | Quyền lợi KH
RQ18 | Nhân viên | Xóa sản phẩm | Xóa sản phảm trong hóa đơn | 2 | trung bình |  | Quyền lợi KH
RQ19 | Nhân viên | Chat tin nhắn | Biết được nhu cẩu của khách hàng như đặt chỗ, hỏi menu,… | 1 | cao |  | Chưa xử lý
RQ20 | Khách hàng | Đặt lại mật khẩu | Đặt lại mật khẩu khi quên | 1 | cao |  | Đã hoàn thành
RQ21 | Khách hàng | Đăng ký tài khoản | Tạo tài khoản | 1 | cao |  | Chưa xử lý
RQ22 | Khách hàng | Đăng nhập | Đăng nhập vào ứng dụng | 1 | cao |  | Chưa xử lý
RQ23 | Khách hàng | Đăng xuất | Đăng xuất khỏi ứng dụng | 1 | cao |  | Chưa xử lý
RQ24 | Khách hàng | Xác nhận mã khuyến mãi | Xác nhận ưu đãi | 2 | trung bình |  | Đang phát triển
RQ25 | Khách hàng | Tìm kiếm sản phẩm | Tìm sản phẩm dễ dàng hơn | 2 | trung bình |  | Chưa xử lý
RQ26 | Khách hàng | Xem chi tiết sản phẩm | Xem sản phảm gồm thành phần gì | 3 | thấp |  | Chưa xử lý
RQ27 | Khách hàng | Sắp xếp danh sách sản phẩm | Sắp xếp theo danh mục như café, nước ép, … | 3 | thấp |  | Chưa xử lý
RQ28 | Khách hàng | Xóa sản phẩm trong giỏ hàng | Xóa sản phẩm đã thêm vào giỏ | 1 | cao |  | Đã hoàn thành
RQ29 | Khách hàng | Thêm sản phẩm vào giỏ hàng | Thêm sản phảm vào giỏ | 1 | cao |  | Đã hoàn thành
RQ30 | Khách hàng | Lịch sử mua hàng | Xem hóa đơn đã đặt từ trước | 2 | trung bình |  | Chưa xử lý
RQ31 | Khách hàng | Hủy đơn hàng | Hủy đơn hàng khi không còn nhu cầu mua | 1 | cao |  | Đã hoàn thành
RQ32 | Khách hàng | Thanh toán online | Thanh toán linh hoạt | 3 | thấp |  | Chưa xử lý
RQ33 | Khách hàng | Đặt hàng online | Đặt hàng mà không cần ra quán | 3 | thấp |  | Chưa xử lý
RQ34 | Khách hàng | Theo dõi đơn hàng | Theo dõi tình trạng đơn hàng | 1 | cao |  | Đã hoàn thành
RQ35 | Khách hàng | Sử dụng mã khuyến mãi | Nhận ưu đãi | 2 | trung bình |  | Đã hoàn thành
RQ36 | Khách hàng | Cập nhập thông tin | Sửa thông tin khách hàng | 1 | cao |  | Đã hoàn thành
RQ37 | Khách hàng | Đánh giá và nhận xét sản phẩm | Đánh giá sản phảm sau khi mua | 3 | thấp |  | Chưa xử lý

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.